## Tabelle1
Risk | Effect | Classification | Strategy
Simulation results are not reproducible | Experimental results cannot be analysed reliable | Delays project / Catastrophic | Analysis and reconfiguration of components which have nonreproducible behaviour
Simulation does not reflect reality | Results of simulation cannot be used because they are show an unexpected behaviour | Delays Project | A more detailed analysis of the real components is needed to get a more precise simulation model
The step from simu-lation to the reality cannot be executed | The level of abstraction is to high | Ignorable / Delays Project | Abstract components which are related to this step have to be refined (A possible solution approach is given with HIL)
Abstraction of a com-ponent cannot be realised because it is unexpected impossible | This planned approach is not feasible and unusable for reali-sation | Catastrophic | The possibility of realisation of each abstraction has to be analysed before the abstraction assumptions are made
MDB framework does not support desired functionality | Scheduled components cannot be realised using MDB framework support | Ignorable / Delays Project | Desired functionality can be implemented in a lower level, like in C/C++ or Matlab language, under consideration of the interfaces of the MDB framework