## Cover
Creation Date | 2012-04-29
Status | Completed
Author | Kah Ho Pau
Identifier | QCM_PP
Current Version | 1.0 | [5 empty] | A
Reviewer Info. | [6 empty] | A
Change History
B
Change |  |  | Changed Chapters | Description | Reason for Change | Revised by | C
No. | Date | Version |  |  |  |  | D

## Project Plan
Calender Week
[5 empty] | March |  | April |  |  |  | May |  |  |  |  | June |  |  |  | Legende
[5 empty] | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | In progress
| What |  |  | Who | [15 empty] | Done
Delay
| Planning | [18 empty] | Stopped
1 | Understand the project | [18 empty] | Now | bar: March 12 to April 15
2 | Kick off | [18 empty] | Holiday
3 | Input testing | [18 empty] | End of project | bar: March 13 to April 15
1st Phase
1 | Control Optimization - changing float variable to integer |  |  | * | [15 empty] | * Delayed and might be cancelled, due to some difficulties at starting
| 1.1 | Figuring a solution from everyone | bar: March 13 to April 16
| 1.2 | Implementing the solution | bar: April 16 to April 17
| 1.3 | Bugs shooting | bar: April 17 to May 18
2 | Remote Parameter Visualisation |  |  | C, Li
| 2.1 | Introduction to xBee | bar: March 13 to May 19
| 2.2 | Interface designing | bar: May 20 to June 24
2nd Phase
1 | Soft landing | bar: May 18 to June 23
| 1.1 | Integrating the ultrasonic sensor
|  | 1.1.1 | Mounting | GX | bar: April 17 to May 18
|  | 1.1.2 | Developing function to read the signal | Yin, GX | bar: May 18 to May 19
| 1.2 | Developing and implementing the strategies |  | All | bar: May 20 to May 22
| 1.3 | Testing | bar: May 22 to June 23
2 | Stay in Position | bar: May 19 to June 23
| 2.1 | Integrating the GPS
|  | 2.1.1 | Mounting | Pau | bar: April 17 to May 18
|  | 2.1.2 | Developing function to read the signal | N, Pau | bar: May 18 to May 19
| 2.2 | Developing and implementing the strategies |  | All | bar: May 20 to May 22
| 2.3 | Testing | bar: May 22 to June 23
3 | Integration and Testing |  |  | C | bar: June 23 to June 24
| Documentation |  |  | All
Members:
| Li | Dongliang Li
| Yin | Yin Hao
| C | Chandana Rokhade
| GX | GuangXun Nan
| Pau | Kah Ho Pau
| N | Nivas Devendran

## Sheet3
Description
Members:
Chandana Rokhade, Dongliang Li, Guangxun Nan, Nivas Dev, Kah Ho Pau, Yin Hao
Flying drone will be quite helpful in a lot of cases, thanks to its agility and size. It can scout out regions which are out of reach for humans or dangerous to humans. For example, scouting in Nuclear Plant Fukushima. The ultimate goal of our project, Quadrocopter, is to create an autonomous drone which is capable to perform scout missions or some simple instructions (like buying pizza) in any landscape. In this semester, we will try to further improve the algorithm used in the microcontroller and install new functions which would lead us to the ultimate goal in future.
At the beginning of the project, we will receive following items from professor:
- Source code
- Quadrocopter which is capable to fly with remote control
- GPS sensor
- Ultrasonic sensor
- Documents from previous groups
- Parameter Visualisation software
At the end of the project, such results should be expected:
- Optimized control
- Timing compare
- Communication between Quadrocopter and PC
- 2 extra functions installed( soft landing, stay in position)
- Installation of sensors onto Quadrocopter